## Burndown Chart
Feature | Initial Estimate | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Hours Left
Data Collection and Analysis | 20 | 5 | 3 | 5 | 1 | 1 | 5
Algorithm and Models | 30 | 5 | 10 | 10 | 3 | 3 | -1
Testing and Verification | 20 | 3 | 3 | 2 | 1 | 0 | 11
Tweaking of Models | 30 | 5 | 1 | 2 | 10 | 5 | 7
Enhancements | 20 | 4 | 5 | 3 | 1 | 1 | 6
Settting | Start | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Planned Hours |  | 15 | 15 | 15 | 15 | 15
Actual Hours |  | 22 | 22 | 22 | 16 | 10
Remaining Effort | 120 | 98 | 76 | 54 | 38 | 28
Ideal Burndown | 120 | 105 | 90 | 75 | 60 | 45